## Sheet1
# | Scenario | Phase | Result | Observation / Fix required
--- | ---------- | ------- | -------- | ----------------------------
1 | Book stores genre and entity_activations | 1 | Fail | Books table status: Is_well_known flag is 0, even though I have filled the name and author of the book in the Is this well known book control Well known author and well_known_book_title not filled Genre field not filled No control for Full / Title workflow types
2 | Artefacts and cover_analysis can be created and retrieved | 1 | Pass
3 | CRUD for artefacts (create, list, update) | 2 | Pass
4 | Cover analysis upsert and GET | 2 | Pass
5 | Artefact–chunk–scene links | 2 | FAIL | Scene-Characters link available in scene_characters table scene_locations - ony 1 record Scene_artefacts table - 0 records Scene table contains empty scenes - Ie. Scenes with no title and no narrative summary
6 | Artefact analysis extracts meaningful objects, not background | 3 | Pass
7 | Artefacts have structure and classification | 3 | Pass
8 | Cover analysis returns thematic statement and mood | 4 | Pass
9 | Genre affects cover recommendations | 4 | Pass
10 | Default entity_activations by genre (cover_only) | 4 | Unsure how to test
11 | Selective analysis by entity_types | 5 | Fail | Selective analysis feature not available in interface - maybe it realization is in later phase (after Phase 6)
12 | Analysis progress shows per-entity status | 5 | Fail | Analysis progress screen is monotonous and does not show progress by entity
13 | Re-trigger single entity type (analyze/entity) | 5 | Fail | Feature not availbale in application
14 | GET/PUT artefacts | 5 | Unsure how to test
15 | GET/PATCH cover-analysis | 5 | Unsure how to test
16 | PUT entity-activations | 5 | Unsure how to test
17 | Proposed search queries include artefacts and cover | 6 | Fail | Search queries page only includes characters, locations and Scenes. Maybe changes required to show search strings for artefacts will be delivered later - check the implementation plan 4.0
18 | Reference search for artefacts only | 6 | Fail | Reference search available for characters and locations only Maybe artefacts search will be availbale in later phases then phase 6
19 | Reference search for cover only | 6 | fail | Reference search available for characters and locations only Maybe cover search will be availbale in later phases then phase 6
20 | Reference-results returns artefacts and cover | 6 | Fail | reference search reslts for artefacts and cover not available in the application yet
21 | Approve with artefact_selections and cover_selections | 6 | Fail | Feature not availbale in application
22 | Reference-upload for artefact and cover | 6 | Fail | Feature not availbale in application
23 | Behance/Dribbble appear in providers list when key set | 6 | PASS | SERPAPI key is enabled